## Sheet1
Unadjusted Actor Weighting Table:
Actor Type | Description | Weighting Factor | Number | Result
Simple | External system with well-defined API | 1 | 0 | 0
Average | External system using a protocol-based 2 0 0 interface, e.g., HTTP, TCT/IP, or a database | 2 | 2 | 4
Complex | Human | 3 | 4 | 12
|  |  | Unadjusted Actor Weight Total (UAW) | 16
Unadjusted Use-Case Weighting Table:
Use Case Type | Description | Weighting Factor | Number | Result
Simple | 1-3 transactions | 5 | 4 | 20
Average | 4-7 transactions | 10 | 5 | 50
Complex | >7 transactions | 15 | 2 | 30
|  |  | Unadjusted Use Case Weight Total (UUCW) | 100
Unadjusted Use-Case Points (UUCP) = UAW + UUCW 116 = 100 +16
Technical Complexity Factors:
Factor Number | Description | Weight | Assigned Value(0-5) | Weighted Value | Notes
T1 | Distributed system | 2 | 2 | 4
T2 | Response time or throughput performance objectives | 1 | 5 | 5
T3 | End-user online efficiency | 1 | 4 | 4
T4 | Complex internal processing | 1 | 0 | 0
T5 | Reusability of code | 1 | 4 | 4
T6 | Ease of installation | 0.5 | 3 | 1.5
T7 | Ease of use | 0.5 | 3 | 1.5
T8 | Portability | 2 | 0 | 0
T9 | Ease of change | 1 | 2 | 2
T10 | Concurrency | 1 | 0 | 0
T11 | Special security objectives included | 1 | 1 | 1
T12 | Direct access for third parties | 1 | 0 | 0
T13 | Special user training required | 1 | 0 | 0
|  |  | Technical Factor Value(Tfactor) | 23
Technical Complexity Factor (TCF) = 0.6 + (0.01 * Tfactor) = 0.6 +(0.01*23) = 0.83
Environmental Factors:
Factor Number | Description | Weight | Assigned Value(0-5) | Weighted Value | Notes
E1 | Familiarity with system development process being used | 1.5 | 4 | 6
E2 | Application experience | 0.5 | 4 | 2
E3 | Object - oriented experience | 1 | 3 | 3
E4 | Lead analyst capability | 0.5 | 5 | 2.5
E5 | Motivation | 1 | 4 | 4
E6 | Requirements stability | 2 | 4 | 8
E7 | Part-time staff | -1 | 0 | 0
E8 | Difficulty of programming langugage | -1 | 2 | -2
|  |  | Environmental Factor Value (Efactor) | 25.5
Environmental Factor(EF) = 1.4 + (-0.03 * Efactor) = 1.4+(-0.03 *25.5) |  |  | 0.635
Adjusted Use Case Points (UCP) = UUCP * TCF * ECF = 116*0.635 |  |  | 61.1378
Effort in person-hours = UCP * PHM = 20*61.1378 |  |  | 1222.756